## Sheet1
DEFECT ID | TEST CASE ID | DEFECT SUMMARY | REPRODUCE STEP | Test data | DEFECT TYPES | DEFECT SEVERITY | DEFECT PRIORITY | expeted result | actual result | TESTER NAME | ATTACHMENT | status
2 | 2 | check login button | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password:secret_sauce | funcationality | high | medium | To open the dashboard properly | as per expected result but not show proper dashboard datlis | KUNAL PATEL | https://drive.google.com/file/d/1lIq64qYk8ksTJo-AxufagbUhl5bNwzfl/view?usp=sharing | OPEN
3 | 3 | check login button with wrong value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:KINHH password:KHHHF | funcationality | high | medium | To display validation message in proper way | as per expected result but not to display properly | KUNAL PATEL | https://drive.google.com/file/d/1gAM6pj01l0weOmsHsdRxCnRrHvojao8K/view?usp=sharing | OPEN
3 | 3 | check login button with blank or null value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password: | funcationality | high | medium | To display validation message in proper way | as per expected result but password is in red only username massage not shown | KUNAL PATEL | https://drive.google.com/file/d/1Yl8Rqear6dswFgfSaifPYYg33zqp5srd/view?usp=sharing | OPEN
3 | 3 | check login button with username is correct and password is with wrong value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password:KING | funcationality | high | medium | To display validation message in proper way | as per expected result but why user name is in redif it is correct | KUNAL PATEL | https://drive.google.com/file/d/1qLrIdEzRzf2_D0CEmXMq-mTEVuq0I58Y/view?usp=sharing | OPEN
6 | 6 | check login button with username is incorect and password is correct | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:dfgbuuyr password:secrect_sauce | funcationality | high | medium | To display validation message in proper way | as per expected result but why password is in red if it is correct | KUNAL PATEL | https://drive.google.com/file/d/1FsIZjv0LEWJNtoySLsMJqRDc2r7u3F1_/view?usp=sharing | OPEN
7 | 7 | check login button with username is blank and password is correct | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:secrect_sauce | funcationality | high | medium | To display validation message in proper way | as per expected result but why password is in red if it is correct | KUNAL PATEL | https://drive.google.com/file/d/1HNFMokZ5Doh4JrqLmkviwTqTqiPqMoaI/view?usp=sharing | OPEN
8 | 8 | check login button with username is correct and password is blank | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standrd_user password: | funcationality | high | medium | To display validation message in proper way | as per expected result but why username is in red if it is correct | KUNAL PATEL | https://drive.google.com/file/d/1F8XEdU7uWhXIjX3egBk-ONqNvNpxOoV-/view?usp=sharing | OPEN
9 | 9 | check login button with white space in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standrd user password: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1cy18FMAcoZu5H6GAviSVJnWUC_-OcFLJ/view?usp=sharing | OPEN
10 | 10 | check login button with special character in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:%%@ password: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1uYFd9x6UUxhhF8nitBpQUNj7CtuWIqo0/view?usp=sharing | OPEN
11 | 11 | check login button with only alpha character in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:kingbbbb password: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1CgQhneWvH05VGariW3GW5pzaqStiQsRz/view?usp=sharing | OPEN
12 | 12 | check login button with only length of username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:kkkkkkkkkkk password: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1DXG45CqqjuHYJdPC14kzHjSFA-finGO_/view?usp=sharing | OPEN
13 | 13 | check login button with only digit of username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:143143 password: | funcationality | HIGH | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1d-sSVeLr-D0IVI786Z0atf7ELMromZrx/view?usp=sharing | OPEN
14 | 14 | check login button with correct username and white space in password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password: | funcationality | high | medium | To display validation message in proper way | as per expated result but why user name is in red. | KUNAL PATEL | https://drive.google.com/file/d/1DBcKxYcBMPpyOsn7lkAt9b0UH4KEi_qF/view?usp=sharing | OPEN
15 | 15 | check login button with only white space of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password: | funcationality | high | Medium | To display validation message in proper way | as per expated result but why only user name is required.and not show proper validation massage in password. | KUNAL PATEL | https://drive.google.com/file/d/1J7IC5LGmCYneFFxEzXQGhcv43Opx-mis/view?usp=sharing | OPEN
16 | 16 | check login button with only special character in password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:#@@## | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1Sp5zl_rxSD-ymRvd0atIvOehlzTdzbH7/view?usp=sharing | OPEN
17 | 17 | check login button with only length of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:dddddddddd | funcationality | high | medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/1pUozJjP_hBvrJbV_iYKC4XXhIfYdC8Ez/view?usp=sharing | OPEN
18 | 18 | check login button with white space between alpha charcter of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password: KUNAL DANGI | funcationality | High | Medium | To display validation message in proper way | not show proper validation massage . | KUNAL PATEL | https://drive.google.com/file/d/14SRyknd8L73v8NVyVrD2lPQXpn0aCOBV/view?usp=sharing | OPEN
19 | 19 | check all item menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click all item menu |  | funcationality | HIGH | HIGH | To display validation message in proper way | Its not redirect to another page | KUNAL PATEL | https://drive.google.com/file/d/1y3Xe88HroVV5K-PWvm60lnIu-Qv22qxA/view?usp=sharing | OPEN
20 | 20 | check about menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click all about menu | NA | funcationality | high | low | To display validation message in proper way | it's is not open the about page and redirct to anthore page. | KUNAL PATEL | https://drive.google.com/file/d/1hJwj0Zb7Ld0od_UMBtP6Wx-yj0mdvYjR/view?usp=sharing | OPEN
21 | 21 | check reset app state menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click on reset app state | NA | funcationality | high | HIGH | To display validation message in proper way | its not doing anything | KUNAL PATEL | https://drive.google.com/file/d/1Er0-C0GxJNPklI0nP9MkWvR0XEjk0ctd/view?usp=sharing | OPEN
22 | 22 | check continue button blank value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button 8)click on checkout button. 9)click on continue button | first name: last name: Zip: | funcationality | high | medium | To display validation message in proper way | as per expted result but why only first name is required;. | KUNAL PATEL | https://drive.google.com/file/d/1z5tmbEiYGFQGDUQbm3XNe4M2SBl5QCvD/view?usp=sharing | OPEN
| 39 | check continue button with blank value of last name and zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: kunal last name: Zip: | funcationality | high | medium | To display validation message in proper way | as per expected result but name was also in red | KUNAL PATEL | https://drive.google.com/file/d/1qKvpZ1wlA-Jv1K8BqoT1v7EgFcUM8QzW/view?usp=sharing | OPEN
40 | 40 | check continue button with blank value of first name and zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: patel Zip: | funcationality | high | medium | To display validation message in proper way | as per expted result but why last name is in red and only first name is required;. | KUNAL PATEL | https://drive.google.com/file/d/1AEDjl8OXoXBqWCHBe_rFdQpSW2YgzfVG/view?usp=sharing | OPEN
41 | 41 | check continue button blank value of first name and last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: patel Zip:0000 | funcationality | high | medium | To display validation message in proper way | as per expted result but why zip code is in red and only first name and lastname is required;. | KUNAL PATEL | https://drive.google.com/file/d/11FJ4SekrKJ9sI9G5_wHWD0KnP5OwPjlC/view?usp=sharing | OPEN
42 | 42 | check continue button with digits in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:12345 last name: Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/15QPl0A6YT53Vl13RmyD8yX6wt9eXsrA0/view?usp=sharing | OPEN
43 | 43 | check continue button with digits in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: 12345 Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1lvjvkztVYme9XZEuCcu63ydZ6feQiZYG/view?usp=sharing | OPEN
| 44 | check continue button with whitespace in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: patel Zip:0000 | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/102KIDASLHMCYu6-Yo6Jx4cujaYI0nJls/view?usp=sharing | OPEN
| 45 | check continue button with whitespace in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: kunal last name: patel Zip:0000 | funcationality | high | medium | To display validation message in proper way | as per expected result but why first name and zip code is in red | KUNAL PATEL | https://drive.google.com/file/d/17GQnShyBaYKtV01trabv073hbVYkYVfh/view?usp=sharing | OPEN
| 46 | check continue button with special character in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: @#$ last name: Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1P_STH1xoE4iJz-bbXV5vi153w9qqFQyO/view?usp=sharing | OPEN
| 46 | check continue button with special character in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: @#$* Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1Mk1fFhyRQeiJ3q46nEImlFqDloxh83Cf/view?usp=sharing | OPEN
| 48 | check continue button with length in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: kkkkkkkk last name: Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1oI8UtMaeFvJ8DLNEd4ThG9CfHP-7XSHw/view?usp=sharing | OPEN
| 49 | check continue button with length in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last namellllllllllllll Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1ysS6M7ZjFUn6PQbEf7kNGEoglHn991uX/view?usp=sharing | OPEN
| 50 | check continue button with alpha charcter and special charcter in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:KU@NA last name: Zip: | funcationality | high | medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1F7_opiexWCVGuSFDZ72YTz3NxRqqQ6hj/view?usp=sharing | OPEN
| 51 | check continue button with alpha charter and special charcter in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: KU@NA Zip: | funcationality | High | Medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/10cSEinGCiDB9i12Ujy5sCjhEZ1VffvXq/view?usp=sharing | OPEN
| 52 | check continue button with digit and alpha charcter in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: KUNAL1234 LAST name: Zip: | funcationality | High | Medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1CBOB9BbIaLT7TXvRisraXkSBBd-50svQ/view?usp=sharing | OPEN
| 53 | check continue button with digit and alpha charcter in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: KUNAL345 Zip: | funcationality | High | Medium | To display validation message in proper way | not show proper validation massage | KUNAL PATEL | https://drive.google.com/file/d/1xNCja_r9dnIxsZFgj7UPHTQMN4g-YBVY/view?usp=sharing | OPEN
| 54 | check continue button with blank value is zip code name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:rahul last name: patel Zip: | funcationality | High | Medium | To display validation message in proper way | as per expactd result but why first name and last name is in red | KUNAL PATEL | https://drive.google.com/file/d/1HlPsTyiow_GhGXb2eom3RTSZR_fGwxCV/view?usp=sharing | OPEN
| 55 | check continue button with blank value is first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: lll Zip:1234 | funcationality | high | medium | To display validation message in proper way | as per expactd result but why zip code and last name is in red | KUNAL PATEL | https://drive.google.com/file/d/18KHYDjqe4dRGO9f1OmzzQktUXLhThJPh/view?usp=sharing | OPEN
| 56 | check continue button with blank value in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:edhidhihs last name: Zip:1234 | funcationality | high | medium | To display validation message in proper way | as per expactd result but why zip code and first name is in red | KUNAL PATEL | https://drive.google.com/file/d/13Z-Al6MOCtOhP-KRUe1HfjNTZJ8BmOCg/view?usp=sharing | OPEN
| 57 | check continue button with alpha charter in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip:KUNAL | funcationality | high | medium | To display validation message in proper way | not show proper validaion massage. | KUNAL PATEL | https://drive.google.com/file/d/1SOaJERR1RPAJs3sc6cR2TWSUyPAQCNAX/view?usp=sharing | OPEN
| 58 | check continue button with spcial charter in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip : @@# | funcationality | High | Medium | To display validation message in proper way | not show proper validaion massage. | KUNAL PATEL | https://drive.google.com/file/d/1GyqbzaX1cVVsGi6vBIvxznUyHwZz9qGY/view?usp=sharing | OPEN
| 59 | check continue button with white space between digits in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip : 123 4 5 | funcationality | high | medium | To display validation message in proper way | not show proper validaion massage. | KUNAL PATEL | https://drive.google.com/file/d/1YK8wr86GU0h4kDauJGoDJQNg0plLbPZj/view?usp=sharing | OPEN
| 60 | check continue button with All wrong value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: 1234r last name: 1234r Zip : 1234t | funcationality | high | medium | to show validation Massage in proper | not show proper validaion massage and also redirct to overview page. | KUNAL PATEL | https://drive.google.com/file/d/1IVs_FkaVrHnBfKwKAxrmd_hHi6eJfqgj/view?usp=sharing | OPEN
| 61 | check continue button with alpha charater in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: kunal last name: kkk Zip : KUNAL | funcationality | high | medium | to show validation Massage in proper | not show proper validaion massage. | KUNAL PATEL | https://drive.google.com/file/d/1KWnxVbhipRWh_tEkfmWSyge0BAqhN4_8/view?usp=sharing | OPEN